## Product Backlog
Product Backlog
Prioritized High-Level User Story List
User Story ID | Priority | Size | As a(n) <type of user> | I want to <perform some task> | So that I can <achieve some goal>.
1 | 1 | Medium | End User | Click a link to view the top five destinations list | See the most popular locations for travel to educate myself on the best places to go.
2 | 2 | large | Frequent Traveler | See a customized list of top destinations based on my profile | Receive relevant recommendations that align with my preferences.
3 | 3 | medium | Budget-Conscious Traveler | Set a price limit for vacation packages | View destinations and deals within my budget.
4 | 4 | large | Traveler with Specific Interests | Set a preferred vacation type, such as cruises or eco-travel | Filter and view options that match my travel style.
5 | 5 | small | Traveler | Exclude irrelevant destinations, such as tropical places, from my suggestions | Focus on destinations I would actually visit.

## User Story Details Example
User Story Number: | 1
User Story Name: | Top Five Destination List
User Story Size: | Medium
User Story Value Statement: | As an end user, I want to click a link to view the top five destinations list, so that I can see the most popular locations for travel to educate myself on the best places to go.
Acceptance Criteria: | • Ability to click link that takes user to a page displaying top destinations • Ordered list of destinations from the most popular location to the fifth-most popular • Each destination on the list will have the following attributes shown: • Destination name • Destination short description (one sentence) • Destination picture • Text with embedded link to take user to top-selling travel package for that location

## User Story Details #1
User Story Number: | 2
User Story Name: | Customized Destination List
User Story Size: | large
User Story Value Statement: | As a frequent traveler, I want to see a customized list of top destinations based on my travel history or profile so that I can receive relevant recommendations that align with my preferences.
Acceptance Criteria: | • Ability to filter destinations by user preferences, including previous travel history and selected categories. • Display a personalized list of top destinations with details such as: • Destination name • Short description • Image • Link to packages and deals. • Option to refine the customization by adjusting preferences. • Ability to save customization preferences for future searches.

## User Story Details #2
User Story Number: | 3
User Story Name: | Budget-Based Destination Filtering
User Story Size: | medium
User Story Value Statement: | As a budget-conscious traveler, I want to set a price limit for vacation packages so that I can view destinations and deals within my budget.
Acceptance Criteria: | • Input field to define a maximum budget for vacation packages. • Results dynamically update to show only destinations and packages within the budget. • Display details for each destination, including: • Name • Price • Image • Link to additional information or booking. • Option to adjust budget without restarting the search. • Include sorting options by price (low-to-high, high-to-low).

## User Story Details #3
User Story Number: | 5
User Story Name: | Destination Exclusion Filtering
User Story Size: | small
User Story Value Statement: | As a traveler, I want to exclude irrelevant destinations, such as tropical places, if they do not match my interests so that I can focus on destinations I would actually visit.
Acceptance Criteria: | • Option to exclude specific types of destinations (e.g., tropical, mountainous, city-based). • Ability to modify exclusion preferences at any time. • Results dynamically update to reflect exclusions. • Saved preferences persist across sessions. • A “clear exclusions” button to reset preferences.